## Estimate
Project Name: |  | SmartLease
Module Name: |  | Sprint 1
Development Team: |  | CS445
Start Date: |  | 2026-09-01
End Date: |  | 2026-09-12
No. | Member Name |  | Estimate
1 | Nam | Trần Văn Sơn Nam | 27 |  |  |  | On Time
2 | Quy | Châu Văn Quy | 34 |  |  |  | Lately
3 | Bin | Phan Tín Bin | 16 |  |  |  | Early
4 | Anh | Đoàn Tuấn Anh | 21 |  |  |  | Unfinished
5 | Hợp | Hoàng Đại Hợp | 16
Total |  |  | 114
SPRINT 1 REPORT | Conponent | Task Name | Resposible Member | Estimate | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12
| Sprint Plan Meeting |  | All member | 5 | 0
| Create Sprint Backlog for Sprint 1 |  | Nam | 5 | 0
| Create Test Plan document for Sprint 1 |  | Nam | 4 | 4 | 0
UI Design
| Design homepage interface |  | Quy | 4 | 4 | 0
| Design article and property listing category interface |  | Quy | 4 | 4 | 0
| Design article view mode within categories |  | Quy | 1 | 1 | 1 | 0
| Design article detail interface |  | Anh | 2 | 2 | 2 | 0
| Design apartment listing detail interface |  | Anh | 2 | 2 | 2 | 0
| Design search results interface |  | Anh | 2 | 2 | 2 | 2 | 0
| Design login interface |  | Nam | 1 | 1 | 1 | 1 | 0
| Design account registration interface |  | Nam | 2 | 2 | 2 | 2 | 0
| Design system notification interface |  | Hợp | 1 | 1 | 1 | 1 | 0
| Design user account dropdown menu |  | Quy | 1 | 1 | 1 | 1 | 1 | 0
| Design personal profile management interface |  | Quy | 1 | 1 | 1 | 1 | 1 | 0
| Design membership subscription and upgrade interface |  | Nam | 3 | 3 | 3 | 3 | 3 | 0
| Design test card payment interface |  | Nam | 1 | 1 | 1 | 1 | 1 | 0
| Design PayPal payment interface |  | Nam | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Design bank transfer and VietQR interface |  | Anh | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Design My Posts management interface |  | Anh | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Design apartment listing creation form |  | Anh | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Design article creation form |  | Anh | 2 | 2 | 2 | 2 | 2 | 2 | 0
Database
| Design database for user accounts, property listings, articles, and images |  | Bin | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Coding Frontend
| (Front-end) Implement homepage and page navigation |  | Quy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| (Front-end) Implement login, registration, and backend error display |  | Nam | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| (Front-end) Implement account menu and logout |  | Quy | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement category interface and switching between article and property listing views |  | Quy | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
| (Front-end) Implement article details, apartment listing details, and image display |  | Anh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
Coding Backend
| (Back-end) Implement account registration |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) Implement login |  | Bin | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| (Back-end) Implement user and administrator authorization |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) Implement listing detail and image retrieval |  | Bin | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| (Back-end) Implement property listing and article browsing |  | Bin | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Testing and Bug Fixing
| Design and execute test cases for UI, accounts, and listing browsing |  | Hợp | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
| Record defects and report test results |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Fix Bug & Release Sprint 2
| Implement test case |  | All member | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
| Fix bugs and report |  | All member | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 0
| Retest after fixing bugs |  | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Closing |  | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  |  | Total | 114 | 104 | 92 | 87 | 81 | 75 | 68 | 53 | 41 | 37 | 29 | 2 | 0

## Actual
Project Name: |  | SmartLease
Module Name: |  | Sprint 1
Development Team: |  | CS445
Start Date: |  | 2026-09-01
End Date: |  | 2026-09-12
No. | Member Name |  | Estimate | Actual
1 | Nam | Trần Văn Sơn Nam | 27 | 27 |  |  |  |  | On Time
2 | Quy | Châu Văn Quy | 34 | 34 |  |  |  |  | Lately
3 | Bin | Phan Tín Bin | 16 | 22 |  |  |  |  | Early
4 | Anh | Đoàn Tuấn Anh | 21 | 21 |  |  |  |  | Unfinished
5 | Hợp | Hoàng Đại Hợp | 16 | 16
Total |  |  | 114 | 120
SPRINT 1 REPORT | Conponent | Task Name | Resposible Member | Actual | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12
| Sprint Plan Meeting |  | All member | 5 | 0
| Create Sprint Backlog for Sprint 1 |  | Nam | 5 | 0
| Create Test Plan document for Sprint 1 |  | Nam | 4 | 4 | 0
UI Design
| Design homepage interface |  | Quy | 4 | 4 | 0
| Design article and property listing category interface |  | Quy | 4 | 4 | 0
| Design article view mode within categories |  | Quy | 1 | 1 | 1 | 0
| Design article detail interface |  | Anh | 2 | 2 | 2 | 0
| Design apartment listing detail interface |  | Anh | 2 | 2 | 2 | 0
| Design search results interface |  | Anh | 2 | 2 | 2 | 2 | 0
| Design login interface |  | Nam | 1 | 1 | 1 | 1 | 0
| Design account registration interface |  | Nam | 2 | 2 | 2 | 2 | 0
| Design system notification interface |  | Hợp | 1 | 1 | 1 | 1 | 0
| Design user account dropdown menu |  | Quy | 1 | 1 | 1 | 1 | 1 | 0
| Design personal profile management interface |  | Quy | 1 | 1 | 1 | 1 | 1 | 0
| Design membership subscription and upgrade interface |  | Nam | 3 | 3 | 3 | 3 | 3 | 0
| Design test card payment interface |  | Nam | 1 | 1 | 1 | 1 | 1 | 0
| Design PayPal payment interface |  | Nam | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Design bank transfer and VietQR interface |  | Anh | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Design My Posts management interface |  | Anh | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Design apartment listing creation form |  | Anh | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Design article creation form |  | Anh | 2 | 2 | 2 | 2 | 2 | 2 | 0
Database
| Design database for user accounts, property listings, articles, and images |  | Bin | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Coding Frontend
| (Front-end) Implement homepage and page navigation |  | Quy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| (Front-end) Implement login, registration, and backend error display |  | Nam | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| (Front-end) Implement account menu and logout |  | Quy | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Front-end) Implement category interface and switching between article and property listing views |  | Quy | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
| (Front-end) Implement article details, apartment listing details, and image display |  | Anh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
Coding Backend
| (Back-end) Implement account registration |  | Bin | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Implement login |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) Implement user and administrator authorization |  | Bin | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Implement listing detail and image retrieval |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) Implement property listing and article browsing |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Testing and Bug Fixing
| Design and execute test cases for UI, accounts, and listing browsing |  | Hợp | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
| Record defects and report test results |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Fix Bug & Release Sprint 2
| Implement test case |  | All member | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
| Fix bugs and report |  | All member | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 0
| Retest after fixing bugs |  | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Closing |  | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  |  | Total | 121 | 111 | 98 | 93 | 87 | 81 | 74 | 74 | 74 | 73 | 51 | 38 | 0

## Chart
Estimate | Actual | Date
104 | 111 | 2026-09-01
92 | 98 | 2026-09-02
87 | 93 | 2026-09-03
81 | 87 | 2026-09-04
75 | 81 | 2026-09-05
68 | 74 | 2026-09-06
53 | 74 | 2026-09-07
41 | 74 | 2026-09-08
37 | 73 | 2026-09-09
29 | 51 | 2026-09-10
2 | 38 | 2026-09-11
0 | 0 | 2026-09-12