## Estimate
Project Name: |  | SmartLease
Module Name: |  | Sprint 2
Development Team: |  | CS445
Start Date: |  | 2026-09-13
End Date: |  | 2026-09-30
No. | Member Name |  | Estimate | [5 empty] | On Time
1 | Nam | Trần Văn Sơn Nam | 32 | [5 empty] | Lately
2 | Quy | Châu Văn Quy | 26 | [5 empty] | Early
3 | Bin | Phan Tín Bin | 26 | [5 empty] | Unfinished
4 | Anh | Đoàn Tuấn Anh | 30
5 | Hợp | Hoàng Đại Hợp | 25
Total |  |  | 139
SPRINT 2 REPORT | Conponent | Task Name | Resposible Member | Estimate | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30
| Sprint Plan Meeting |  | All member | 8 | 0
| Create Sprint Backlog for Sprint 2 |  | Nam | 7 | 0
| Create Test Plan document for Sprint 2 |  | Nam | 6 | 6 | 0
Design UI
| Design Mapbox integration within the apartment listing creation form |  | Anh | 1 | 1 | 0
| Design admin reporting and statistics interface |  | Hợp | 3 | 3 | 3 | 0
| Design detailed statistics and data filtering interface |  | Hợp | 1 | 1 | 1 | 0
| Design feedback interface within reporting and statistics |  | Hợp | 1 | 1 | 1 | 0
| Design report export format selection interface |  | Hợp | 1 | 1 | 1 | 1 | 0
| Design Premium package management and transaction approval interface |  | Anh | 3 | 3 | 3 | 3 | 0
| Design service package editing form |  | Anh | 2 | 2 | 2 | 2 | 0
| Design new service package creation form |  | Anh | 2 | 2 | 2 | 2 | 2 | 0
| Design rating and comment management interface |  | Nam | 3 | 3 | 3 | 3 | 3 | 0
| Design member management interface |  | Quy | 3 | 3 | 3 | 3 | 3 | 0
| Design new member creation form |  | Quy | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Design user profile interface for administrators |  | Quy | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Design system post management interface |  | Anh | 3 | 3 | 3 | 3 | 3 | 3 | 0
Database
| Design database for comments, ratings, membership packages, and transactions |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Coding Frontend
| (Front-end) Implement apartment listing creation and image selection |  | Anh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement article creation |  | Anh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement management, editing, and deletion of personal articles and property listings |  | Anh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Front-end) Implement personal profile viewing and editing |  | Quy | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement comments, replies, and listing ratings |  | Nam | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement search results and filtering using loaded listing data |  | Anh | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| (Front-end) Implement success messages, error messages, and action confirmations |  | Hợp | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Front-end) Implement membership subscription, upgrades, and status tracking |  | Nam | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Front-end) Implement test card payment flow |  | Nam | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement PayPal flow and transaction request creation |  | Nam | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement bank transfer and VietQR display with transaction request submission |  | Anh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement member management and user profile viewing |  | Quy | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Front-end) Implement new member creation form |  | Quy | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement system article and property listing management |  | Anh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement feedback display using rating and comment data |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Coding Backend
| (Back-end) Implement property listing and article creation |  | Bin | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Implement post editing and deletion |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) Implement personal profile updates |  | Bin | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| (Back-end) Implement listing ratings |  | Bin | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| (Back-end) Implement membership subscription and status tracking |  | Bin | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Implement password changes |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) Implement comments and replies |  | Bin | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Testing and Bug Fixing
| Design and execute test cases for post creation, post management, and search |  | Hợp | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Test personal profiles, password changes, comments, and ratings |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Test membership packages and simulated payment flows |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Test member management, post management, and feedback interfaces |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Record defects and report test results |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Fix backend and database defects |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Fix frontend defects |  | Quy, Nam, Anh | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
Fix Bug & Release Sprint 2
| Implement test case |  | All member | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
| Fix bugs and report |  | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Retest after fixing bugs |  | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Closing |  | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  |  | Total | 139 | 124 | 117 | 112 | 106 | 98 | 91 | 85 | 78 | 71 | 65 | 58 | 52 | 47 | 42 | 39 | 32 | 2 | 0
Task Name
Design Mapbox integration within the apartment listing creation form
Design admin reporting and statistics interface
Design detailed statistics and data filtering interface
Design feedback interface within reporting and statistics
Design report export format selection interface
Design Premium package management and transaction approval interface
Design service package editing form
Design new service package creation form
Design rating and comment management interface
Design member management interface
Design new member creation form
Design user profile interface for administrators
Design system post management interface
Database
Design database for comments, ratings, membership packages, and transactions
Coding Frontend
(Front-end) Implement apartment listing creation and image selection
(Front-end) Implement article creation
(Front-end) Implement management, editing, and deletion of personal articles and property listings
(Front-end) Implement personal profile viewing and editing
(Front-end) Implement comments, replies, and listing ratings
(Front-end) Implement search results and filtering using loaded listing data
(Front-end) Implement success messages, error messages, and action confirmations
(Front-end) Implement membership subscription, upgrades, and status tracking
(Front-end) Implement test card payment flow
(Front-end) Implement PayPal flow and transaction request creation
(Front-end) Implement bank transfer and VietQR display with transaction request submission
(Front-end) Implement member management and user profile viewing
(Front-end) Implement new member creation form
(Front-end) Implement system article and property listing management
(Front-end) Implement feedback display using rating and comment data
Coding Backend
(Back-end) Implement property listing and article creation
(Back-end) Implement post editing and deletion
(Back-end) Implement personal profile updates
(Back-end) Implement listing ratings
(Back-end) Implement membership subscription and status tracking
(Back-end) Implement password changes
(Back-end) Implement comments and replies
Testing and Bug Fixing
Design and execute test cases for post creation, post management, and search
Test personal profiles, password changes, comments, and ratings
Test membership packages and simulated payment flows
Test member management, post management, and feedback interfaces
Record defects and report test results
Fix backend and database defects
Fix frontend defects

## Actual
Project Name: |  | SmartLease
Module Name: |  | Sprint 2
Development Team: |  | CS445
Start Date: |  | 2026-09-13
End Date: |  | 2026-09-30
No. | Member Name |  | Estimate | Actual |  |  |  |  | On Time
1 | Nam | Trần Văn Sơn Nam | 32 | 32 |  |  |  |  | Lately
2 | Quy | Châu Văn Quy | 26 | 26 |  |  |  |  | Early
3 | Bin | Phan Tín Bin | 26 | 33 |  |  |  |  | Unfinished
4 | Anh | Đoàn Tuấn Anh | 30 | 30
5 | Hợp | Hoàng Đại Hợp | 25 | 25
Total |  |  | 139 | 146
SPRINT 2 REPORT | Conponent | Task Name | Resposible Member | Actual | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30
| Sprint Plan Meeting |  | All member | 8 | 0
| Create Sprint Backlog for Sprint 2 |  | Nam | 7 | 0
| Create Test Plan document for Sprint 2 |  | Nam | 6 | 6 | 0
Design UI
| Design Mapbox integration within the apartment listing creation form |  | Anh | 1 | 1 | 0
| Design admin reporting and statistics interface |  | Hợp | 3 | 3 | 3 | 0
| Design detailed statistics and data filtering interface |  | Hợp | 1 | 1 | 1 | 0
| Design feedback interface within reporting and statistics |  | Hợp | 1 | 1 | 1 | 0
| Design report export format selection interface |  | Hợp | 1 | 1 | 1 | 1 | 0
| Design Premium package management and transaction approval interface |  | Anh | 3 | 3 | 3 | 3 | 0
| Design service package editing form |  | Anh | 2 | 2 | 2 | 2 | 0
| Design new service package creation form |  | Anh | 2 | 2 | 2 | 2 | 2 | 0
| Design rating and comment management interface |  | Nam | 3 | 3 | 3 | 3 | 3 | 0
| Design member management interface |  | Quy | 3 | 3 | 3 | 3 | 3 | 0
| Design new member creation form |  | Quy | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Design user profile interface for administrators |  | Quy | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Design system post management interface |  | Anh | 3 | 3 | 3 | 3 | 3 | 3 | 0
Database
| Design database for comments, ratings, membership packages, and transactions |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Coding Frontend
| (Front-end) Implement apartment listing creation and image selection |  | Anh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement article creation |  | Anh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement management, editing, and deletion of personal articles and property listings |  | Anh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Front-end) Implement personal profile viewing and editing |  | Quy | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement comments, replies, and listing ratings |  | Nam | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement search results and filtering using loaded listing data |  | Anh | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| (Front-end) Implement success messages, error messages, and action confirmations |  | Hợp | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Front-end) Implement membership subscription, upgrades, and status tracking |  | Nam | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Front-end) Implement test card payment flow |  | Nam | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement PayPal flow and transaction request creation |  | Nam | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement bank transfer and VietQR display with transaction request submission |  | Anh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement member management and user profile viewing |  | Quy | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Front-end) Implement new member creation form |  | Quy | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement system article and property listing management |  | Anh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Front-end) Implement feedback display using rating and comment data |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Coding Backend
| (Back-end) Implement property listing and article creation |  | Bin | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| (Back-end) Implement post editing and deletion |  | Bin | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Implement personal profile updates |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) Implement listing ratings |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) Implement membership subscription and status tracking |  | Bin | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| (Back-end) Implement password changes |  | Bin | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Implement comments and replies |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Testing and Bug Fixing
| Design and execute test cases for post creation, post management, and search |  | Hợp | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Test personal profiles, password changes, comments, and ratings |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Test membership packages and simulated payment flows |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Test member management, post management, and feedback interfaces |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Record defects and report test results |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Fix backend and database defects |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Fix frontend defects |  | Quy, Nam, Anh | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
Fix Bug & Release Sprint 2
| Implement test case |  | All member | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
| Fix bugs and report |  | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Retest after fixing bugs |  | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Closing |  | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  |  | Total | 146 | 131 | 124 | 119 | 113 | 105 | 98 | 98 | 98 | 98 | 98 | 89 | 76 | 67 | 55 | 44 | 32 | 2 | 0

## Chart
Estimate | Actual | Date
124 | 131 | 2026-09-13
117 | 124 | 2026-09-14
112 | 119 | 2026-09-15
106 | 113 | 2026-09-16
98 | 105 | 2026-09-17
91 | 98 | 2026-09-18
85 | 98 | 2026-09-19
78 | 98 | 2026-09-20
71 | 98 | 2026-09-21
65 | 98 | 2026-09-22
58 | 89 | 2026-09-23
52 | 76 | 2026-09-24
47 | 67 | 2026-09-25
42 | 55 | 2026-09-26
39 | 44 | 2026-09-27
32 | 32 | 2026-09-28
2 | 2 | 2026-09-29
0 | 0 | 2026-09-30