## Estimate
Project Name: |  | SmartLease
Module Name: |  | Sprint 3
Development Team: |  | CS445
Start Date: |  | 2026-10-01
End Date: |  | 2026-10-12
No. | Member Name |  | Estimate
1 | Nam | Trần Văn Sơn Nam | 14 |  |  |  | On Time
2 | Quy | Châu Văn Quy | 15 |  |  |  | Lately
3 | Bin | Phan Tín Bin | 23 |  |  |  | Early
4 | Anh | Đoàn Tuấn Anh | 14 |  |  |  | Unfinished
5 | Hợp | Hoàng Đại Hợp | 14
Total |  |  | 80
SPRINT 3 REPORT | Conponent | Task Name | Resposible Member | Estimate | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12
| Sprint Plan Meeting |  | All member | 3 | 0
| Create Sprint Backlog for Sprint 3 |  | Nam | 3 | 0
| Create Test Plan document for Sprint 3 |  | Nam | 4 | 4 | 0
Design UI
Database
| Add tag tables, tag-to-listing relationships, and listing coordinates |  | Bin | 3 | 3 | 0
Coding Frontend
| (Front-end) Implement comment and rating management, editing, and deletion |  | Nam | 3 | 3 | 0
| (Front-end) Implement Premium package management |  | Anh | 4 | 4 | 4 | 0
| (Front-end) Implement membership transaction approval and rejection |  | Anh | 1 | 1 | 1 | 0
| (Front-end) Implement AI tag display below apartment listing titles |  | Anh | 1 | 1 | 1 | 0
| (Front-end) Implement clickable tags and frontend tag filtering |  | Quy | 2 | 2 | 2 | 2 | 0
| (Front-end) Integrate verification code sending, entry, and email verification during registration |  | Hợp | 2 | 2 | 2 | 2 | 0
| (Front-end) Integrate Mapbox location selection during apartment listing creation |  | Anh | 1 | 1 | 1 | 1 | 0
| (Front-end) Integrate location maps into apartment listing details |  | Anh | 1 | 1 | 1 | 1 | 1 | 0
| (Front-end) Implement report format selection and export |  | Hợp | 1 | 1 | 1 | 1 | 1 | 0
| (Front-end) Implement statistics and data filtering using existing APIs |  | Hợp | 2 | 2 | 2 | 2 | 2 | 0
Coding Backend
| (Back-end) Implement user account management |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) Implement property listing and article management |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) Implement membership package management |  | Bin | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Implement membership transaction approval |  | Bin | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| (Back-end) Implement automatic AI tagging for property listings |  | Bin | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Implement listing search by tag |  | Bin | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| (Back-end) Implement Mapbox integration |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) Implement email verification during registration |  | Bin | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| (Back-end) Implement listing location storage for Mapbox |  | Bin | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Testing and Bug Fixing
| Test account, listing, comment, and rating management |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Test Premium package management and transaction approval |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Test AI tag generation, tag display, and listing search by tag |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Test email verification and listing locations on Mapbox |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Test statistics, data filtering, and report export |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Implement Test Cases & Execute Testing |  | All member | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
| Fix bugs and report issues found during testing |  | All member | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 0
| Retest after fixing bugs |  | All member | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Closing |  | All member | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  | Total | 80 | 74 | 64 | 58 | 53 | 49 | 41 | 37 | 33 | 30 | 16 | 1 | 0

## Actual
Project Name: |  | SmartLease
Module Name: |  | Sprint 3
Development Team: |  | CS445
Start Date: |  | 2026-10-01
End Date: |  | 2026-10-12
No. | Member Name |  | Estimate | Actual
1 | Nam | Trần Văn Sơn Nam | 14 | 14 |  |  |  |  | On Time
2 | Quy | Châu Văn Quy | 15 | 15 |  |  |  |  | Lately
3 | Bin | Phan Tín Bin | 23 | 23 |  |  |  |  | Early
4 | Anh | Đoàn Tuấn Anh | 14 | 14 |  |  |  |  | Unfinished
5 | Hợp | Hoàng Đại Hợp | 14 | 14
Total |  |  | 80 | 80
SPRINT 3 REPORT | Conponent | Task Name | Resposible Member | Actual | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12
| Sprint Plan Meeting |  | All member | 3 | 0
| Create Sprint Backlog for Sprint 3 |  | Nam | 3 | 0
| Create Test Plan document for Sprint 3 |  | Nam | 4 | 4 | 0
Design UI
Database
| Add tag tables, tag-to-listing relationships, and listing coordinates |  | Bin | 3 | 3 | 0
Coding Frontend
| (Front-end) Implement comment and rating management, editing, and deletion |  | Nam | 3 | 3 | 0
| (Front-end) Implement Premium package management |  | Anh | 4 | 4 | 4 | 0
| (Front-end) Implement membership transaction approval and rejection |  | Anh | 1 | 1 | 1 | 0
| (Front-end) Implement AI tag display below apartment listing titles |  | Anh | 1 | 1 | 1 | 0
| (Front-end) Implement clickable tags and frontend tag filtering |  | Quy | 2 | 2 | 2 | 2 | 0
| (Front-end) Integrate verification code sending, entry, and email verification during registration |  | Hợp | 2 | 2 | 2 | 2 | 0
| (Front-end) Integrate Mapbox location selection during apartment listing creation |  | Anh | 1 | 1 | 1 | 1 | 0
| (Front-end) Integrate location maps into apartment listing details |  | Anh | 1 | 1 | 1 | 1 | 1 | 0
| (Front-end) Implement report format selection and export |  | Hợp | 1 | 1 | 1 | 1 | 1 | 0
| (Front-end) Implement statistics and data filtering using existing APIs |  | Hợp | 2 | 2 | 2 | 2 | 2 | 0
Coding Backend
| (Back-end) Implement user account management |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) Implement property listing and article management |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) Implement membership package management |  | Bin | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Implement membership transaction approval |  | Bin | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| (Back-end) Implement automatic AI tagging for property listings |  | Bin | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Implement listing search by tag |  | Bin | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| (Back-end) Implement Mapbox integration |  | Bin | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) Implement email verification during registration |  | Bin | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| (Back-end) Implement listing location storage for Mapbox |  | Bin | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Testing and Bug Fixing
| Test account, listing, comment, and rating management |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Test Premium package management and transaction approval |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Test AI tag generation, tag display, and listing search by tag |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Test email verification and listing locations on Mapbox |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Test statistics, data filtering, and report export |  | Hợp | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Implement Test Cases & Execute Testing |  | All member | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
| Fix bugs and report issues found during testing |  | All member | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 0
| Retest after fixing bugs |  | All member | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Closing |  | All member | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  | Total | 80 | 74 | 64 | 58 | 53 | 49 | 41 | 37 | 33 | 30 | 16 | 1 | 0

## Chart
Estimate | Actual | Date
74 | 74 | 2026-10-01
64 | 64 | 2026-10-02
58 | 58 | 2026-10-03
53 | 53 | 2026-10-04
49 | 49 | 2026-10-05
41 | 41 | 2026-10-06
37 | 37 | 2026-10-07
33 | 33 | 2026-10-08
30 | 30 | 2026-10-09
16 | 16 | 2026-10-10
1 | 1 | 2026-10-11
0 | 0 | 2026-10-12